## Rudrajit
WHY: To reduce environmental impact of LLM and highlight sustainable LLM lifecycle
WEEK NO. | WHAT | TASKS | SUB-TASKS | COMMENTS | ESTIMATE
1 | Starting the project with a particular task - creating a model to estimate whether a review is good or bad and we want to know the carbon emissions and performance upon training and testing of a standard fine-tuned BERT. This provides us with a baseline benchmark which we are going to improve upon. | Dataset & Environment Setup | • Download IMDb dataset • Split into training and testing • Tokenize to feed into transformer |  | 1 Day
|  | Fine-tune BERT (for sentiment analysis) | • Load BERT-base-uncensored model • Set hyperparams like no. of epochs, learning rate, batch size • Train and evaluate using performance metrics like precision, recall, accuracy and F1 score and make confusion matrix • Hyperparameter tuning |  | 2 Days
|  | Carbon Tracking & Metrics | • Integrate CodeCarbon for tracking training carbon emissions data • log all data and metrics |  | 2 Days
|  | Inference on local machine | Provide different prompts and track carbon emission for inference |  | 1 Day
2 | Apply model pruning optimization technique on fine-tuned BERT and verify whether it fares better than the standard model. This shall provides us with proof that model optimization does reduce carbon footprint as well. However, we also keep in mind the performance of the optimized model so as to compare the reduction or increase in performance measure. | Learn how to implement model pruning | • Code a tutorial model pruning to familiarize with it • Learn how to implement model pruning on a fine-tuned model |  | 2 days
|  | Implement Model Pruning on fine-tuned BERT | • Apply both unstructured and structured pruning • Evaluate using performance metrics |  | 1 day
|  | Metrics Logging | • Integrate CodeCarbon and measure carbon emission data • Log performance and carbon emissions data |  | 1 day
|  | Inference on local machine | Provide different prompts and track carbon emissions on inference |  | 1 Day
3 | This is the part where Cloud comes into the picture. We move our models from local testing to the cloud deployment phase. Now we actually try verify our hypothesis that model optimization as well as sustainable cloud configuration can work together to reduce the carbon emissions. We also see how much of a hit accuracy and other performance metrics might take. | Dockerization | Create a Docker file for both standard and pruned model as well as a basic web UI to work as an inference |  | 1 day
|  | Cloud Run Deployment | • Build Docker image for both models • Upload to Artifacts registry • Deploy model on Cloud Run |  | 1 day
|  | Measure Metrics | • Go to Cloud Run service to get metrics like cold start latency, response time • Compare energy estimates using GCP's Carbon Footprint tool |  | 1 day
4 | This is where we visualize the whole picture and see the actual numbers. We compare how the both model fare against each other in terms of carbon emissions and performance of training, inference and cloud deployment and maintainence. | Analyze Results | Compile all performance metrics and carbon emissions data |  | 1 day
|  | Visualize Trade-offs | Create graphs/tables: accuracy vs. energy, etc. |  | 1 day
|  | Write MVP Report | Summary of findings, insights |  | 1 day

## Debarshi
WHAT :Real Time Trade Settlement for the US Market
WHY : Reduce settlement time from T+1 to T+0 using AI, LLMs and DLT
WEEK NO. | TASKS | NEED FOR THE TASK | SUB-TASKS | COMMENTS | ESTIMATE
1 | Blockchain & Token Setup | -Setup a blockchain local PC like Hyperledger Besu - Besu because of its immutability and IBFT-2 consensus which is important for the stock market | - Run Besu on Docker - Create test accounts & fund wallets | Need better understanding of fundamentals of blockchain | 0.5 Day
| ERC-20 & ERC-1400 Contracts | - ERC-20 as a substitute to represent cash and ERC-1400 to represent assets | - Write TokenizedCash.sol (ERC-20)- Write TokenizedSecurity.sol (ERC-1400) - Unit test |  | 1.5 Days
| Atomic Swap Contract | - Atomic Swap is the main idea of this system, this ensures the entire trade is executed or not at all | - Write and test AtomicSwap.sol(contract) with trade tracking, confirmation, DvP |  | 1 Day
| Deployment & Verification | - Deploy contracts to make sure, they are logically correct and transfer of tokens/cash is happening with proper logs | - Deploy contracts to Besu - Verify events, approve + execute test swaps |  | 1 Day
| Hardhat + Script Infra | -Once task is completed with dummy accounts, create real accounts with key and adequate funds/tokens to simulate real market | - Create deployment + test scripts - Set up local wallet/key mgmt |  | 1 Day
2 | AI Agent Integration (Validation) | -Using LangGraph, design AI Agents which will do pre trade checking to ensure buyer has enough funds and seller has enough tokens | - Design Agent to check: balance, compliance |  | 1 Day
| Agent Actions + Simulation | -If the conditions are satisfied, proceed with the trade -If there is a shortage of funds on the buyer's side, invoke a contract to give a loan | - Allow Agent to auto-approve/reject- Simulate liquidity fallback (token loan/ smart contract logic) |  | 1 Day
| LLM Reporting (Trade Summary) | In accordance with FINRA, as all trades must be explainable | - Call Gemini API or locally run Llama 3 to explain trades - Format compliance summary/logs |  | 1 Day
| RAG + Vector Search Setup | In case the LLM doesn't do well on we need RAG for better performance | - Index sample SEC policies- Set up FAISS/Qdrant for retrieval |  | 1 Day
3 | Event Logging + Automation | Keep Track of all events and monitor those events via Python's web3 library or ether.js | - Add SwapExecuted, SwapFailed events- Set up listener via web3.py |  | 1 Day
| Post-Settlement Trigger | After a trade has been executed, the log book must be updated to reflect the changes | - Trigger logging or treasury update on events |  | 1 Day
| Dockerization + Local Test | Containerize for cloud deployement | - Create Dockerfile - Compose Besu containers |  | 1 Day
4 | Metrics Dashboard (Optional) | Check trade stats like number of successful/unsuccessful trades, latency, average trade settlement duration | - Log trade stats using python, latency |  | 1 Day
| Compliance Testing | To check if all the extreme cases are covered, to mimick the real world uncertainities | - Simulate edge cases: conduct trades using blacklisted traders, underfunded accounts |  | 1 Day
| Final Report + Visualization |  | - Tabulate results- Explain system architecture, challenges, findings |  | 1 Day